## Slide 1
Project Management:
A Systems Approach to
Planning, Scheduling, and Controlling
Thirteenth Edition

## Slide 2
Chapter One
Overview

## Slide 3: Overview of Project Management
TIME
COST
PERFORMANCE/TECHNOLOGY
RESOURCES

## Slide 4: Project Characteristics
Have a specific objective (which may be unique or one of a kind) to be completed within certain specifications
Have defined start and end dates
Have funding limits (if applicable)
Consume human and nonhuman resources (i.e., money, people, equipment)
Be multifunctional (cut across several functional lines)

## Slide 5: Project Management
Project planning
  Definition of work requirements
  Definition of quantity and quality of work
  Definition of resources needed
Project monitoring
  Tracking progress
  Comparing actual outcome to predicted outcome
  Analyzing impact
  Making adjustments

## Slide 6: PROJECT MANAGEMENT IS THE ART OF CREATING THE ILLUSION THAT ANY OUTCOME IS THE RESULT OF A SERIES OF PREDETERMINED, DELIBERATE ACTS WHEN IN FACT IT WAS DUMB LUCK !

## Slide 7: The Talent Triangle
Technical project management
Leadership
Strategic and business management

## Slide 8: Multiple Boss Reporting
GM
PM
LM
LM
LM
APM
APM
SPONSOR
PM = Project Manager
APM = Assistant Project Manager
LM = Line or Functional Manager

## Slide 9: WHY USE PROJECT MANAGEMENT?

## Slide 10: Project management and productivity are related!

## Slide 11
MATURITY IN PROJECT MANAGEMENT IS LIKE A THREE-LEGGED STOOL.
THE LEGS REPRESENT THE:
Project manager
Line manager(s)
Executive management (i.e., project sponsor)
Maturity cannot exist without stability

## Slide 12: The Three-Legged Stool
Project
Manager
Line
Management
Management
Senior
(i.e., Sponsor)

## Slide 13
TOP OF THE THREE-LEGGED STOOL
ORGANIZATIONAL
STRUCTURE
ORGANIZATIONAL
BEHAVIOR
TOOLS &
TECHNIQUES

## Slide 14
How important is project management training?
Part-time project management–
is it good or bad?
Critical Questions

## Slide 15: Role of the Project Manager

## Slide 16: Negotiating for Resources

## Slide 17: The Project Kickoff Meeting

## Slide 18: Establishing the Project’s Policies and Procedures

## Slide 19: Laying Out the Project Workflow and Plan

## Slide 20: Establishing Performance Targets

## Slide 21: Obtaining Funding

## Slide 22: Executing the Plan

## Slide 23: Acting as the Conductor

## Slide 24: Putting Out Fires

## Slide 25: Counseling and Facilitation

## Slide 26: Encouraging the Team to Focus on Deadlines

## Slide 27: Monitoring Progress by “Pounding the Pavement”

## Slide 28: Evaluating Performance

## Slide 29: Develop Contingency Plans

## Slide 30: Briefing the Project Sponsor

## Slide 31: Briefing the Team

## Slide 32: Briefing the Customer

## Slide 33: Closing Out the Project

## Slide 34: Why Is a Project Management System Necessary?

## Slide 35: Project Management
Time
Resources
Cost
Quality/Technology

## Slide 36: Benefits
Identification of functional responsibilities to ensure that all activities are accounted for, regardless of personnel turnover
Minimizing the need for continuous improvement
Identification of time limits for scheduling
Identification of a methodology for trade-off analysis
Measurement of accomplishment against plans

## Slide 37: Benefits (continued)
Early identification of problems so that corrective action can follow
Improved estimating capability for future planning
Knowing when objectives cannot be met or will be exceeded

## Slide 38: Obstacles
Project complexity
Customer’s special requirements and scope changes
Organizational restructuring
Project risks
Changes in technology
Forward planning and pricing

## Slide 39: Humor
Project management is the art of creating the illusion that any outcome is the result of a series of predetermined, deliberate acts when, in fact, it was dumb luck.

## Slide 40: Classical Management
Planning
Organizing
Staffing
Controlling
Directing
Which of the above is usually NOT
performed by the project manager?

## Slide 41: Resources
Money
Manpower
Equipment
Facilities
Materials
Information/technology

## Slide 42: Successful Culture
A good daily working relationship between the project manager and those line managers who directly assign resources to projects
The ability of functional employees to report vertically to their line manager at the same time they report horizontally to one or more project managers

## Slide 43: Interface Management
Managing human interrelationships within the project team
Managing human interrelationships between the project team and the functional organization
Managing human interrelationships between the project team and senior management
Managing human interrelationships between the project team and the customer’s organization, whether an internal or external organization

## Slide 44: As part of interface management, the project manager’s role also includes integration management.

## Slide 45: Integration Management
Integrated Processes
Capital
Materials
Equipment
Facilities
Information
Personnel
Resources
Inputs
Integration Management
Products
Services
Profits
Outputs

## Slide 46: The Functional Role
The functional manager has the responsibility to define how the task will be done and where the task will be done (i.e., the technical criteria).
The functional manager has the responsibility to provide sufficient resources to accomplish the objective within the project’s constraints (i.e., who will get the job done).

## Slide 47: Functional Obstacles
Unlimited work requests (especially during competitive bidding)
Predetermined deadlines
All requests having a high priority
Limited number of resources
Limited availability of resources
Unscheduled changes in the project plan
Unpredicted lack of progress

## Slide 48: Functional Obstacles (continued)
Unpredicted lack of progress
Unplanned absence of resources
Unplanned breakdown of resources
Unplanned loss of resources
Unplanned turnover of personnel

## Slide 49: Most projects also have a project sponsor, who may or may not reside at the executive level of management.

## Slide 50: The Project Sponsor Interface
Project Team
Project Manager
Project Manager
Project Sponsor
Objective setting
Up-front planning
Project organization
Key staffing
Master plan
Policies
Monitoring execution
Priority-setting
Conflict resolution
Executive-client contact
Relationship:
Project Sponsor: Lower/Middle Management
Project Sponsor: Senior Management
Priority Projects
Maintenance Projects

## Slide 51: Project Necessities
Complete task definitions
Resource requirement definitions (and possibly skill levels needed)
Major timetable milestones
Definition of end-item quality and reliability requirements
The basis for performance measurement

## Slide 52: Results of Good Planning
Assurance that functional units will understand their total responsibilities toward achieving project needs
Assurance that problems resulting from scheduling and allocation of critical resources are known beforehand
Early identification of problems that may jeopardize successful project completion so that effective corrective action and replanning can occur to prevent or resolve problems

## Slide 53: Promises Made???
Promotion
Grade
Salary
Bonus
Overtime
Responsibility
Future work assignments

## Slide 54: Project Managers vs. Champions
Project Managers | Project Champions
Prefer to work in groups | Prefer working individually
Committed to their managerial and technical responsibilities | Committed to technology
Committed to the corporation | Committed to the profession
Seek to achieve the objective | Seek to exceed the objective
Are willing to take risks | Are unwilling to take risks; try to test everything
Seek what is possible | Seek perfection
Think in terms of short time spans | Think in terms of long time spans
Manage people | Manage things
Are committed to and pursue material values | Are committed to and pursue intellectual values

## Slide 55: Project Management in Non-Project-Driven Groups
Projects may be few and far between.
Not all projects have the same project management requirements, and therefore they cannot be managed identically. This difficulty results from poor understanding of project management and a reluctance of companies to invest in proper training.
Executives do not have sufficient time to manage projects themselves, yet refuse to delegate authority.

## Slide 56: Project Management in Non-Project-Driven Groups (Continued)
Projects tend to be delayed because approvals most often follow the vertical chain of command. As a result, project work stays too long in functional departments.
Because project staffing is on a “local” basis, only a portion of the organization understands project management and sees the system in action.
There exists heavy dependence on subcontractors and outside agencies for project management expertise.

## Slide 57: High-Level Reporting
The project manager is charged with getting results from the coordinated efforts of many functions. He or she should, therefore, report to the person who directs all those functions.
The project manager must have adequate organizational status to do his or her job effectively.
To get adequate and timely assistance in solving problems that inevitably appear in any important project, the project manager needs direct and specific access to an upper echelon of management .

## Slide 58: High-Level Reporting (Continued)
The customer, particularly in a competitive environment, will be favorably impressed if his or her project manager reports to a high organizational echelon.

## Slide 59: Low-level Reporting
It is organizationally and operationally inefficient to have too many projects, especially small ones, diverting senior executives from more vital concerns.
Although giving a small project a high place in the organization may create the illusion of executive attention, its real result is to foster executive neglect of the project.
Placing a junior project manager too high in the organization will alienate senior functional executives on whom he or she must rely for support.

## Slide 60
DELEGATION
OF AUTHORITY TO
PROJECT MANAGER
EXECUTIVE
MEDDLING
LACK OF UNDERSTANDING OF HOW PROJECT
MANAGEMENT SHOULD WORK
LACK OF TRAINING IN COMMUNICATIONS /
INTERPERSONAL SKILLS
THE TIP-OF-THE-ICEBERG SYNDROME
MANY OF THE PROBLEMS ASSOCIATED WITH PROJECT MANAGEMENT WILL
SURFACE MUCH LATER IN THE PROJECT AND RESULT IN MUCH HIGHER COSTS

## Slide 61
Project vs. Functional Influences
Project Influence
in Decision Making
Dual Influence
Functional
Organization
Matrix
Project
Organization
Relative Influence
Functional Influence
In Decision Making
Organization