## Slide 1
Project Management:
A Systems Approach to
Planning, Scheduling, and Controlling
Thirteenth Edition

## Slide 2
Chapter Two
Project Management
Growth: Concepts and
Definitions

## Slide 3: When to Use Project Management
Are the jobs complex?
Are there dynamic environmental considerations?
Are the constraints tight?
Are there several activities to be integrated?
Are there several functional boundaries to be crossed?

## Slide 4: The Need For Restructuring
Accomplish tasks that could not be effectively handled by the traditional structure
Accomplish onetime activities with minimum disruption to routine business

## Slide 5: Restructuring Problems
Project priorities and competition for talent may interrupt the stability of the organization and interfere with its long-range interests by upsetting the normal business of the functional organization.
Long-range planning may suffer as the company gets more involved in meeting schedules and fulfilling the requirements of temporary projects.

## Slide 6: Restructuring Problems (continued)
Shifting people from the project to project may disrupt the training of new employees and specialists. This may hinder their growth and development within their fields of specialization.

## Slide 7: Imperatives
The time span between project initiation and completion appears to be increasing.
The capital committed to the project prior to the use of the end item appears to be increasing.
As technology increases, the commitment of time and money appears to become inflexible.

## Slide 8: Imperatives (Continued)
Technology requires more and more specialized manpower.
The inevitable counterpart of specialization is organization.
The above five “imperatives” identify the necessity for more effective planning, scheduling, and control.

## Slide 9: Obstacles
Unstable economy
Shortages
Soaring costs
Increased complexity
Heightened competition
Technological changes
Societal Concerns
Consumerism
Ecology
Quality of work

## Slide 10: Results of NOT Controlling Obstacles
Decreased Profits
Increased manpower needs
Cost overruns, schedule delays, and penalty occurring earlier and earlier
An inability to cope with new technology
R&D results too late to benefit existing product lines
Temptation to make hasty decisions that prove to be costly

## Slide 11: Results of NOT Controlling Obstacles (Continued)
Management insisting on earlier and greater return on investment
Greater difficulty in establishing on-target objectives in real time
Problems in relating cost to technical performance and scheduling during the execution of the project

## Slide 12: Project Management Growth
Technology increasing at an astounding rate
More money invested in R&D
More information available
Shortening of project life cycles

## Slide 13: Early Reasons For Failure
There was no need for project management.
Employees were not informed about how project management should work.
Executives did not select the appropriate projects or project managers for the first few projects.

## Slide 14: Early Reasons for Failure (Continued)
There was no attempt to explain the effect of the project management organizational structure on the wage and salary administration program.
Employees were not convinced that executives were in total support of the change (to project management).

## Slide 15: Integrative Responsibility
Total accountability assumed by a single person
Project rather than functional dedication
A requirement for coordination across functional interfaces
Proper utilization of integral planning and control

## Slide 16: Advantages
Easy adaptation to an ever-changing environment
Ability to handle a multidisciplinary activity within a specified period of time
Horizontal as well as vertical work flow
Better orientation toward customer problems
Easier identification of activity responsibilities
A multidisciplinary decision-making process
Innovation in organizational design

## Slide 17: Project Management Evolution
Biblical Project Management
Military Project Management
Space Exploration
Heavy Construction
Other

## Slide 18: Life Cycle Phases for Project Management Maturity
Line Management Acceptance
Growth
Maturity
Embryonic
Executive Management Acceptance

## Slide 19: Life Cycle Phases for Level 2 Project Management Maturity
Executive Management Acceptance
Line Management Acceptance
Growth
Maturity
Embryonic
Recognize need
Recognize benefits
Recognize applications
Recognize what must be done

## Slide 20: Life Cycle Phases for Level 2 Project Management Maturity
Embryonic
Line Management Acceptance
Growth
Maturity
Executive
Management
Acceptance
Visible executive support
Executive understanding of project management
Project sponsorship
Willingness to change way of doing business

## Slide 21: Life Cycle Phases for Level 2 Project Management Maturity
Executive Management Acceptance
Line Management Acceptance
Growth
Maturity
Line Management Acceptance
Line management support
Line management commitment
Line management education
Willingness to release employees for project management training

## Slide 22: Life Cycle Phases for Level 2 Project Management Maturity
Executive Management Acceptance
Line Management Acceptance
Growth
Maturity
Embryonic
Growth
Development of a methodology
Use of life cycle phases
Commitment to planning
Minimization of “creeping scope”
Selection of a project tracking system

## Slide 23: Life Cycle Phases for Level 2 Project Management Maturity
Embryonic
Line Management Acceptance
Growth
Maturity
Maturity
Development of a management cost/ schedule control system
Integrating cost and schedule control
Developing an educational program to enhance project management skills

## Slide 24: Driving Forces for Maturity
Capital projects
Customer expectations
Competitiveness
Executive understanding
New product development
Efficiency and effectiveness

## Slide 25: The Components of Survival
Efficiency and Effectiveness
New Product Development
Executive Understanding
Capital Projects
Customer Expectations
Competitiveness
SURVIVAL

## Slide 26: The Speed of Maturity
Internal
Efficiencies &
Effectiveness
Fast
Slow
Speed of Maturity
Project-Driven
Organizations
Non-Project-Driven
and Hybrid
Organizations
Customer
Expectations
Competitiveness

## Slide 27: Benefits of Project Management
Project management will require more people and add to the overhead costs.
Profitability may decrease.
Project management allows us to accomplish more work in less time and with fewer people.
Profitability will increase.
Past View
Present View

## Slide 28: Benefits of Project Management
Project management will increase the number of scope changes.
Project management creates organizational instability and increases conflicts.
Project management will provide better control of scope changes.
Project management makes the organization more efficient and effective.
Past View
Present View

## Slide 29: Benefits of Project Management
Project management is really “eye wash” for the customer’s benefit.
Project management will create problems.
Project management will allow us to work more closely with our customers.
Project management provides a means for problem solving.
Past View
Present View

## Slide 30: Benefits of Project Management
Only large projects need project management.
Project management will increase quality problems.
All projects will benefit from project management.
Project management increases quality.
Past View
Present View

## Slide 31: Benefits of Project Management
Project management will create power and authority problems.
Project management focuses on suboptimization by looking at only the project.
Project management will eliminate the majority of the power struggles.
Project management allows people to make good company decisions.
Past View
Present View

## Slide 32: Benefits of Project Management
Project management delivers products to a customer.
The cost of project management may make us uncompetitive.
Project management delivers solutions to a customer.
Project management will increase our business.
Past View
Present View

## Slide 33: Project Management Costs versus Benefits
$
?
Time
Additional Profits from Better Project Management
Cost of Project Management
Pegged

## Slide 34: Industry Classification (by Project Management Utilization)
Project -Driven
PM has P&L responsibility
PM is a recognized profession
Multiple career paths
Income comes from projects
Hybrid
Production driven but with many projects
Emphasis on new product develop.
Short product life cycles
Marketing-orient.
Need for rapid develop. process
Program Management
Very few projects
Profitability from production
Large brick walls
Long life cycle products
Product Management
Present
Past
Project Management
Non-
Project-Driven

## Slide 35: From Hybrid to Project-Driven
Entrance via project-driven divisions such as MIS and R&D
Entrance via marketing, sales, engineering, and R&D
Traditional Project
Management
Modern Project
Management
1960-1990 Hybrid
1990-Present Hybrid

## Slide 36: Recessionary Effects
Recession
Layoffs
R&D
Training
Solutions Sought
Results of the Recessions
1979-1983
Blue Collar
Eliminated
Eliminated
Short Term
Return to status quo
No project management support
No allies for project management
Change way of doing business
Risk management
Examine lessons learned
1989-1993
White Collar
Focused
Focused
Long Term
Characteristics

## Slide 37: New Processes Supporting Project Management
1960- 1985
1985
1990
1991- 1992
1993
1994
No Allies
Total Quality Manage- ment
Concurrent Engineering
Empower- ment and Self- Directed Teams
Re- Engineering
Life Cycle Costing
Increasing Support

## Slide 38: New Processes Supporting Project Management (Continued)
1995
1996
1997-
1998
1999
2000
Scope
Change
Control
Risk
Management
Project
Offices
And
COEs
Co- Located
Teams
Multi-
national
Teams
Increasing Support

## Slide 39: New Processes Supporting Project Management (Continued)
2001
2002
2003
2004
2005
Maturity
Models
Strategic
Planning
For
Project
Management
Intranet
Status
Reports
Capacity
Planning
Models
Six Sigma Project Mgmt.
Increasing Support

## Slide 40: New Processes Supporting Project Management (Continued)
2006
2007
2008
2009
Virtual Project Teams
Lean
Project Teams
Best
Practice
Libraries
Capacity
Planning
Models
Increasing Support

## Slide 41: New Processes Supporting Project Management (Continued)
2010
2011
2012
2013
Complex
Projects
Committee
Governance
From Triple to Competing Constraints
Advances in New Metrics and Dashboards
Increasing Support

## Slide 42: New Processes Supporting Project Management (Continued)
2014
2015
2016-
2017
2018
Value-Driven Project Mgt.
Global Project Management & Cultures
Merger & AcquisitionProject Mgmt.
?
Increasing Support

## Slide 43: Definitions: Systems
Air Force
  A composite of equipment, skills, and techniques capable of performing and/or supporting an operational role. A complete system includes related facilities, equipment, material services, and personnel required for its operation to the degree that it can be considered as a self-sufficient unit in its intended operational and/or support environment.

## Slide 44: Definitions: Systems (continued)
NASA
  One of the principal functioning entities comprising the project hardware within a project or program. The meaning may vary to suit a particular project or program area. Ordinarily, a “system” is the first major subdivision of project work (spacecraft systems, launch vehicle systems).

## Slide 45: Definitions: Programs
Air Force
  The integrated, time-phased tasks necessary to accomplish a particular purpose.
NASA
  A series of undertakings that continue over a period of time (normally years) and that are designed to accomplish a broad, scientific or technological goal in the NASA long-range plan (lunar and planetary exploration, manned spacecraft systems).

## Slide 46: Definitions: Projects
NASA/Air Force
  A project is within a program as an undertaking with a scheduled beginning and end, and which normally involves some primary purpose.

## Slide 47
KINDS OF PROJECTS
Once a group of tasks is selected and considered to be a project, the next step is to define the kinds of projects encountered. There are four categories of projects:
INDIVIDUAL PROJECTS
Short-duration projects normally assigned to a single individual, who may be acting as a project manager and/or a functional manager.
STAFF PROJECTS
These projects that can be accomplished by one organizational unit, say a department. Staff (or a task force) is developed from each section involved. This works best when one functional unit is involved.

## Slide 48
SPECIAL PROJECTS
Very often special projects occur that require that certain primary functions and/or authority be assigned temporarily to other individuals or unit. These works best for short-duration projects. Long-term projects can lead to severe conflicts.
MATRIX OR AGGREGATE PROJECTS
These projects require specific (or specialized) input from a large number of functional (or business) units and usually control vast resources.

## Slide 49
Failures
Projects
Time
Successes
MATURITY
EXCELLENCE
2 YEARS
5 YEARS
Successes vs. Failures

## Slide 50: Evolution of Policies, Procedures and Guidelines
Magnitude of Documentation
LEGEND
1970s
Early 1980s
Mid-1980s
Late 1980s
1990s
Project
Management
with Concurrent
Engineering
CONVENTIONAL PROJECT MANAGEMENT
Life Cycle Phases
Policy and Procedure Manuals
Guidelines per Life Cycle Phase
General Project Guidelines
Checklists with Periodic Review Points

## Slide 51: DEFINITION OF A PROJECT LIFE CYCLE
Resources
Utilized
RESOURCES
TIME
CONCEPTUAL
PHASE
DETAILED PLANNING PHASE
FEASIBILITY AND
PRELIMINARY PLANNING PHASE
IMPLEMENTATION
PHASE
CONVERSION
OR TERMINATION PHASE
PMO
PMO *

## Slide 52: Success: Point or Cube?
Cost
Quality
(or scope)
Time

## Slide 53
The Definition of Success

## Slide 54: Success
Definition of Success
  Primary factors
    Within time
    Within cost
    Within quality
    Accepted by the customer

## Slide 55: Success
  Secondary factors:
    Customer reference
    Follow-on work
    Financial success
    Technical superiority
    Strategic alignment
    Regulatory agency relations
    Health and safety
    Environmental protection
    Corporate reputation
    Employee alignment
    Ethical conduct

## Slide 56: Success
Critical Success Factors (CSFs) [Focuses on the deliverables]
Key Performance Indicators (KPIs) [Focuses on the execution metrics of the process]

## Slide 57: Definitions
Factor | Traditional Definition | Future Definition
Project | A temporary endeavor undertaken to create a unique product, service, or result | A collection of sustainable business value scheduled for realization
Program | Achieving a set of business goals through the coordinated management of interdependent projects over a finite period of time | A collection of projects designed to achieve a business purpose and create sustainable business value within the established competing constraints
Success | Completion of the projects or programs within the triple constraints of time, cost, and scope | Achieving the desired business value within the competing constraints

## Slide 58
Key Performance Indicators
These are shared learning topics that allow us to maximize what we do right and correct what we do wrong.

## Slide 59: Components of Failure
None
A
Perceived Failure
Actual
Planned
Perfection
Achievable
B
C
D
Actual Failure
Planning Failure
E
Accomplishment

## Slide 60: Components of Failure
None
A
Perceived Failure
Actual
Planned
Perfection
Achievable
B
C
D
Actual Failure
Planning Failure
E
Accomplishment

## Slide 61: Degrees of Success & Failure
Complete
Success
Partial
Success
Partial
Failure
Complete
Failure

## Slide 62: Degrees of Success & Failure
Complete
Success
The expected business
value is achieved within
all of the competing
constraints.

## Slide 63: Degrees of Success & Failure
Partial
Success
Some or all of the
expected business value
is achieved but not
within all of the
competing constraints.

## Slide 64: Degrees of Success & Failure
Partial
Failure
The only achievable
business value is some
intellectual property that
may be useful on future
projects.

## Slide 65: Degrees of Success & Failure
Complete
Failure
The project may have
been canceled or simply
not completed, and no
business value, benefits
or intellectual property is
indicated. Also, the end
result may not have
performed correctly.

## Slide 66: Risk Planning
Poor Risk Management
Technical Inability
Customer Expectations
Actual Performance
Performance
Time

## Slide 67: Mitigation Strategies Available
Opportunities for Trade-offs Resulting from Risk Analyses
Project Objectives
Project Planning
Schedule Risk Assessment
Financial Risk Assessment
Technical Risk Assessment and Forecasting
Market Risk Assessment and Forecasting
Project Execution
Numerous
Limited
Technical Strategy
Product/Market Strategy

## Slide 68
The starting point in the development of any project management methodology is the implementation of a
stage-gate process.

## Slide 69: Stages
Groups of series or parallel activities (based upon the risks of the project)
Managed by cross-functional teams
To reach a predetermined deliverable established by management

## Slide 70: Gates
Structured decision points at the end of each stage
Number of gates must be limited

## Slide 71: Gatekeepers
Individuals (i.e., sponsors) or groups of individuals assigned by senior management
Empowered to enforce the structured process (including change management)
Authorized to evaluate performance and make decisions
And willing to provide the team necessary technical and business information

## Slide 72: Gatekeeper’s Decisions
Proceed to next gate with the original objectives
Proceed to the next gate with revised objectives
Delay making a gate decision until further information is obtained
Terminate the project

## Slide 73: Stage-Gate Failures
Assigning gatekeepers and not empowering them to make decisions
Assigning gatekeepers who are afraid to terminate a project
Failure to provide the team with information critical to gate reviews
Allowing the team to focus more on the gates than on the stages

## Slide 74: Methodology Inputs
Project Management Methodology
Organization
Work (Tasks)
Tools
People

## Slide 75: Methodologies Can Fail
Methodologies can fail when they:
Are abstract and high level
Contain insufficient narratives to support these methodologies
Are not functional or do not address crucial areas
Ignore the industry standards and best practices
Look impressive but lack real integration into the business
Use nonstandard project conventions and terminology
Compete for similar resources without addressing this problem
Don’t have any performance metrics
Take too long to complete because of bureaucracy and administration

## Slide 76: Resistance to Change
Low
Neutral
High
Finance
H.R.
Eng.
I.T.
Sales
Marketing
Procurement
Manu.
R&D

## Slide 77: Change Process
Support for Change
Time
Denial
Resistance
Exploration
Resistance
Support

## Slide 78: Types of Cultures
Cooperative
Noncooperative
Isolated (large companies)
Fragmented (multinational)

## Slide 79: Integrated Processes for The 21st Century
Project Management
Concurrent
Engineering
Risk
Management
Change
Management
Total Quality
Management

## Slide 80: Integrated Processes (Past, Present, and Future)
Yrs: 1990-2000
Project management
Total quality management
Concurrent engineering
Scope change management
Risk management
Yrs: 2000-2017
Supply chain management
Business processes
Feasibility studies
Cost-benefit analyses (ROI)
Capital budgeting
Integrated
Processes
Integrated
Processes
Current
Integrated
Processes

## Slide 81: Knowledge Repositories
PM Best
Practices
PM Best
Practices
Libraries
Knowledge
Repositories
(PM and
Business
Knowledge)
Integration of Business
Processes into the EPM
Methodology
Time
Quantity of Information
Project Knowledge
Base (PKB) or Technical Knowledge Base (TKB)

## Slide 82: Multiproject Management
Are the project objectives the same?
  For the good of the project?
  For the good of the company?
Is there a distinction between large and small projects?
How do we handle conflicting priorities?
  Critical versus critical projects
  Critical versus noncritical projects
  Noncritical versus noncritical projects