## Slide 1: Fun with Network Diagrams
Dr. Ram Arthanari

## Slide 2: Question 1
Question 1: Given the following tasks and dependencies, draw a network diagram and calculate the critical path.
Task A: 2 days
Task B: 4 days (depends on Task A)
Task C: 3 days (depends on Task A)
Task D: 5 days (depends on Task B)
Task E: 1 day (depends on Task C)
Task F: 3 days (depends on Task D and Task E)

## Slide 3: Answer
To determine the critical path, start by drawing out the tasks and their dependencies. You'll find the critical path by identifying the longest path through the network.
Task A -> Task B -> Task D -> Task F
Critical Path: A (2 days) -> B (4 days) -> D (5 days) -> F (3 days) = 14 days

## Slide 4: Question 2
Question 2: Provide a network diagram for a project with the following
tasks and their dependencies. Identify any possible parallel tasks.
Task A: Start
Task B: 5 days (depends on Task A)
Task C: 6 days (depends on Task A)
Task D: 2 days (depends on Task B and Task C)
Task E: 4 days (depends on Task B)
Task F: 3 days (depends on Task C)
Task G: End (depends on Task D, Task E, and Task F)

## Slide 5: Answer
Identify any possible parallel tasks based on the dependencies provided.
Tasks B and C can start simultaneously after Task A.
Tasks D, E, and F can run in parallel after B and C.
Diagram:
  Task A ->
  (Task B and Task C in parallel) ->
  (Task D, Task E, Task F in parallel) -> Task G
  Parallel tasks: B & C, D & E & F

## Slide 6: Question 3
Question 3: Using the network diagram below,
Calculate the earliest start (ES), earliest finish (EF), latest start (LS), and latest finish (LF) for each task.
Task A: 0 days (Start)
Task B: 5 days (depends on Task A)
Task C: 2 days (depends on Task B)
Task D: 3 days (depends on Task B)
Task E: 1 day (depends on Task C and Task D)
Task F: 2 days (depends on Task D)

## Slide 7: Answer
Use a forward and backward pass to calculate ES, EF, LS, and LF
for each task.
Task A: ES = 0, EF = 0, LS = 0, LF = 0
Task B: ES = 0, EF = 5, LS = 0, LF = 5
Task C: ES = 5, EF = 7, LS = 5, LF = 7
Task D: ES = 5, EF = 8, LS = 5, LF = 8
Task E: ES = 8, EF = 9, LS = 8, LF = 9
Task F: ES = 8, EF = 10, LS = 8, LF = 10

## Slide 8: Question 4
Question 4: Draw a network diagram based on the following tasks and
their durations. Identify the float for each task.
Task A: 2 days
Task B: 3 days (depends on Task A)
Task C: 4 days (depends on Task A)
Task D: 6 days (depends on Task B and Task C)
Task E: 2 days (depends on Task D)
Task F: 1 day (depends on Task E)

## Slide 9: Answer
Calculate the float for each task by identifying the difference between the latest start and earliest start.
Task A: Float = 0
Task B: Float = 0
Task C: Float = 0
Task D: Float = 0
Task E: Float = 0
Task F: Float = 0