## Slide 1: Project Planning: Scope and the Work Breakdown Structure

## Slide 2: Learning Objectives
Understand and describe the relationship among scope, schedule, and budget.
Understand the processes and apply several tools for defining and managing the scope of a project.
Understand the difference between project scope (i.e. project deliverables) and product scope (i.e. features and functionality of the product or system).
Develop a Work Breakdown Structure (WBS).
Differentiate between an deliverable and a milestone.
Describe and apply several project estimation methods.

## Slide 3: Introduction
Scope –
  defines the work boundaries and deliverables of the project so what needs to get done, gets done – and only what needs to get done, gets done.
  is determined directly by the project’s MOV.
  Defines all the work, activities, and deliverables that the project team much provide for the project to achieve its MOV
Work Breakdown Structure – a project management tool that provides a hierarchical structure that acts as a bridge, or link, between the project’s scope and the detailed project plan that will be created.

## Slide 4: Figure 5.1 – The Triple Constraint

## Slide 5: Scope Management Processes
Plan Scope Management
  Defines and Documents how the project and product scope will be defined, verified, and changed if necessary.
Collect Requirements
  Defining and documenting the customer, sponsor, or stakeholder needs and expectations. This may be a formal document.
Define Scope
  A detailed description of the product, service, or information system to be designed, built and implemented. A detailed scope statement defines what work will and will not be part of the project and will serve as a basis for all future project decisions
Create the Work Breakdown Structure
  The decomposition or dividing of the major project deliverables (i.e., scope) into smaller and more manageable components
Validate Scope
  Confirmation and formal acceptance that the project’s scope is accurate, complete, and supports the project’s MOV. The project team and sponsor must agree to all deliverables
Control Scope
  Ensuring that controls are in place to manage proposed scope changes once the project’s scope is set. Must be communicated to all project stakeholders.

## Slide 6: Figure 5.2 – Scope Management Plan

## Slide 7: Figure 5.3 – Scope Boundary

## Slide 8: Statement of Work (SOW)
Narrative description of the product, service, or information system.
For internal projects, this is tied to the business need
For external projects,
  this would include specifications, quantities, quality standards, and performance requirements for prospective bidders and
  The SOW is often included in a document that may be called a request for proposal (RFP), request for information (RFI), or request for bid (RFB).

## Slide 9: Scope Statement
Examples of Scope Statements
Develop a proactive electronic commerce strategy that identifies the processes, products and services to be delivered through the World Wide Web.
Develop an application system that supports all of the processes, products, and services identified in the electronic commerce strategy.
The application system must integrate with the bank’s existing enterprise resource planning system.
A scope statement is another way to define the scope boundary; it is a detailed documentation of the sponsor’s needs and expectations.

## Slide 10: Scope
Project-Oriented Scope
  Support the project management processes defined by the Project Life Cycle (PLC) and the chosen project methodology.
  Deliverable Structure Chart (Figure 5.4 – DSC) – a tool used by the project manager and team.
Product-Oriented Scope
  Specific features and functionality of the application system
  First cut of requirements definition
  Use Case Diagram (Figure 5.5) – a system modeling tool used for refining the scope boundary and defining what the system must do.

## Slide 11: Out of Scope
Technology and organizational assessment of the current environment
Customer resource management and data mining components

## Slide 12: Project Scope Definition
The scope boundary and scope statement provide a useful first step
The project’s scope must now be defined in more detail in terms of specific deliverables that provide a basis for developing the project’s work breakdown structure (WBS)
Tools:
  Deliverable Definition Table
  Deliverable Structure Chart
  Context Level Data Flow Diagram
  Use Case Diagram

## Slide 13
Figure 5.4 – Deliverable
Structure Chart

## Slide 14
Figure 5.5 – Use Case
Diagram

## Slide 15: Validate Scope
Verification of the MOV
  Has the project’s MOV been clearly defined and agreed upon?
Documentation of All Deliverables
  Are the deliverables tangible and verifiable?
  Do they support the project’s MOV?
Specification of Quality Standards
  Are controls in place to ensure that the work was not only completed but completed to meet specific standards?
Identification of Milestones
  Are milestones defined for each deliverable?
Review and Acceptance
  Are both sides clear in their expectations?

## Slide 16: Control Scope and Scope Change Control Procedures
Concerned with managing changes to the project’s scope and to ensure that these changes are beneficial when they occur
Potential Issues:
  Scope Grope
  Scope Creep
  Scope Leap
Procedures:
  Scope Change Request Form (Figure 5.6)
  Scope Change Request Log (Figure 5.7)

## Slide 17
Figure 5.6 – Scope Change Request Form

## Slide 18
Figure 5.7 – Scope Change Request Log

## Slide 19: Work Breakdown Structure (WBS)
The PMBOK® Guide states that the WBS represents a logical decomposition of the work to be performed and focuses on how the product, service, or result is naturally subdivided. It is an outline of what work is to be performed.

## Slide 20: Figure 5.8 – Work Package

## Slide 21: Deliverables versus Milestones
Deliverables
  Tangible, verifiable work products
    Reports, presentations, prototypes, etc.
Milestones
  Significant events or achievements
  Acceptance of deliverables or phase completion
  Cruxes (proof of concepts)
  Quality control
  Keeps team focused

## Slide 22: Developing the WBS (Figure 5.4 repeated)
A work package is developed for each of the phases and deliverables defined in the Deliverable Structure Chart (DSC)

## Slide 23: Deliverable: Test Results Report
Logical Activities:
  Review the test plan with the client so that key stakeholders are clear as to what will be tested, how the tests will be conducted, and when the tests will be carried out.
  Carry out the tests as outlined in the plan.
  Once the test results are collected, we need to analyze them.
  The results should be summarized in the form of a report and presentation to the client.
  If all goes well, the client will sign-off or approve the test results and then we can move on to the implementation phase of the project. If not, then we need to address and fix any problems.
What are the deliverables? Milestones?

## Slide 24: Example Work Breakdown Schedule

## Slide 25: Figure 5.9 – Work Package and Work Breakdown Structure

## Slide 26: Things to Keep in Mind When developing the WBS…
Should support the project’s MOV
Should be “deliverable-oriented”
The level of detail should support planning and control
Developing the WBS should involve those who will be doing the work

## Slide 27: Estimation Questions
How do you estimate?
What are you going to estimate?
Where do you start?

## Slide 28: Estimation Techniques - Traditional Project Management Approaches
Guesstimating
Delphi Technique
Time Boxing
Top-Down
Bottom-Up
Poker Planning

## Slide 29
Guestimating
Estimation by guessing or just picking numbers out of the air is not the best way to derive a project’s schedule and budget. Unfortunately, many inexperienced project managers tend to guesstimate, or guess at the estimates, because it is quick and easy.

## Slide 30: Delphi Technique
Involves multiple, anonymous experts
Each expert makes an estimate
Estimates compared
  If close, can be averaged
  If not, do another iteration until consensus is reached

## Slide 31: Time Boxing
Often used on Agile projects
A “box” of time is allocated for a specific activity, task, or deliverable
Can focus a team if used effectively
Can demoralize a team if not used effectively

## Slide 32: Top-Down
Top & middle managers determine overall project schedule &/or cost
Lower level managers are expected to breakdown schedule/budget estimates into specific activities (WBS)

## Slide 33: Bottom-Up
Schedules & budgets are constructed from WBS
Starts with people who will be doing the work
Schedules & budgets are the aggregate of detailed activities & costs
May use analogous estimation – developing estimates based on one’s opinion that there is a significant similarity between the current project and others.

## Slide 34: Poker Planning
Variation of Delphi Technique
Uses a deck of cards that represents an estimate in days
Moderator describes particular task, feature, deliverable, or user story to be estimated.
Attempts to reach consensus in a few rounds of “play”